## v2.2
Appendix P-3b: Integrated Design Process Matrix
B3 State of Minnesota Sustainable Building Version 2.2
ACTIVITIES |  | PROJECT PHASE | [8 empty] | TEAM MEMBERS RESPONSIBILITIES "R" represents Responsible Party & "x" represents participant
"R" represents Responsible Party "x" represents Participating Party
|  | Agency Planning | Pre-Design - Programming | Pre-Design - Site Selection | Schematic Design | Design Development | Construction Documents | Construction | Correction Period | On-Going Operations | Cx Leader | Facilities Operations Manager (FOM) | Project Manager | Designers | Contractors | Energy Modeler | Guideline Leader
1. GENERAL INTEGRATED DESIGN PROCESS TASKS
1.01 | Conduct Organization/Kick Off Meeting |  |  |  | x | [5 empty] | R | x | x |  |  |  | x
1.02 | Review Site Alternatives |  |  | x | [6 empty] | R |  |  | x
1.03 | Engage Commissioning Team |  |  |  | x | [5 empty] | R | x | x | x |  | x | x
1.04 | Design Intent Document |  | x | x | x | x | x |  |  |  | x | x | R |  |  | x
1.05 | Basis of Design |  | x | x | x | x | x |  |  |  | x |  | x | R |  | x
2. CONSTRUCTION PHASE AIR QUALITY MANAGEMENT
2.01x | Construction Air Quality Management Plan | [5 empty] | x | x | [5 empty] | x | R
2.02 | Protect Stored Materials | [6 empty] | x | [6 empty] | R
2.03 | Protect Filtration Materials | [6 empty] | x | [6 empty] | R
2.04 | Temporary Construction Ventilation | [6 empty] | x | [6 empty] | R
2.05 | Protect HVAC System | [6 empty] | x | [6 empty] | R
2.06 | Offsite Product Preconditioning | [6 empty] | x | [6 empty] | R
2.07 | Remove Moisture Damaged Materials | [6 empty] | x | [6 empty] | R
2.08 | Protect Porous Materials | [6 empty] | x | [6 empty] | R
2.09 | Building Flush-out Period | [6 empty] | x | [6 empty] | R
2.10 | Pre-assessment of Existing Building Indoor Air Quality Problems |  | x |  |  |  |  | x |  |  |  | x | x | x | R
2.11 | Protect Occupants in Adjacent Building Areas During Construction | [6 empty] | x |  |  |  | x |  |  | R
3. CORRECTION PERIOD AIR QUALITY MANAGEMENT
3.01 | Correction Period Air Quality Management Plan | [5 empty] | x | [7 empty] | R
3.02 | 3 Month Building Air Quality Evaluation & Modifications | [7 empty] | x | [5 empty] | R
3.03 | 6 Month Building Air Quality Evaluation & Modifications | [7 empty] | x | [5 empty] | R
3.04 | 10 Month Building Air Quality Evaluation & Modifications | [7 empty] | x | [5 empty] | R
4. CONSTRUCTION WASTE MANAGEMENT
4.01 | Construction Waste Management Specification | [5 empty] | x | x | [5 empty] | x | R
4.02 | Construction Waste Management Plan | [6 empty] | x | [6 empty] | R
4.03 | Debris Diversion | [13 empty] | R
4.04 | Recyclable Packaging | [13 empty] | R
4.05 | Hazardous Waste | [13 empty] | R