## v2.2
Appendix P-4b: Design and Construction Commissioning Matrix
B3 State of Minnesota Sustainable Building Version 2.2
ACTIVITIES |  | PROJECT PHASE | [8 empty] | TEAM MEMBERS RESPONSIBILITIES "R" represents Responsible Party & "x" represents participant
"R" represents Responsible Party "x" represents Participating Party
|  | Agency Planning | Pre-Design - Programming | Pre-Design - Site Selection | Schematic Design | Design Development | Construction Documents | Construction | Correction Period | On-Going Operations | Cx Leader | Facilities Operations Manager (FOM) | Project Manager | Designers | Contractors | Energy Modeler | Guideline Leader
1. GENERAL
1.01 | Design & Construction Phase Commissioning Plan | x | x | x | x | x | x | x |  |  | R
1.02 | Commissioning Reports |  | x | x | x | x | x | x | x |  | R
1.03 | Review Compliance & Outcome Documentation for SB2030 | x | x | x | x | x | x | x | x |  | R |  | x | x |  | x
2. SYSTEMS COMMISSIONING
2.01 | Engage Commissioning Team |  |  |  | x | [5 empty] | R | x | x | x |  | x | x
2.02 | Coordination of Design Intent Document |  | x | x | x | x | x |  |  |  | x | x | R |  |  | x
2.03 | Coordination of Basis of Design Document |  | x | x | x | x | x |  |  |  | x |  | x | R |  | x
2.04 | Commissioning Design Review |  |  |  | x | x | x |  |  |  | R |  |  | x
2.05 | Coordinate with Operations Commissioning Requirements (P.5) |  |  |  | x | x | x | x | x |  | R | x | x | x | x | x
2.06 | List of I/O Data Points | [5 empty] | x | [6 empty] | R
2.07 | Incorporate Cx Criteria & Scope into Construction Documents | [5 empty] | x |  |  |  | x |  |  | R
2.08 | Review Contractors' Submittals | [6 empty] | x |  |  | R |  |  | x | x
2.09 | Verify Installation | [6 empty] | x |  |  | R |  |  |  | x
2.10 | Verify Functional Performance | [6 empty] | x |  |  | R |  |  |  | x
2.11 | Verify O&M Documentation | [6 empty] | x |  |  | R |  |  |  | x
2.12 | Verify O&M Training | [6 empty] | x |  |  | R | x |  |  | x
2.13 | Systems Operations Manual | [6 empty] | x |  |  | R |  |  | x | x | x
2.14 | Deferred Verification | [7 empty] | x |  | R |  |  |  | x
2.15 | Ten Month O&M Review | [7 empty] | x |  | R | x | x | x | x