## v2.2
Appendix P-5b: Operations Commissioning Matrix
B3 State of Minnesota Sustainable Building Guidelines version 2.2
ACTIVITIES |  | PROJECT PHASE | [8 empty] | TEAM MEMBERS RESPONSIBILITIES
"R" represents Responsible Party "x" represents Participating Party
|  | Agency Planning | Pre-Design - Programming | Pre-Design - Site Selectin | Schematic Design | Design Development | Construction Documents | Construction | Correction Period | On-Going Operations | Cx Leader | Facilities Operations Manager (FOM) | Designers | Contractors | Energy Modeler | Guideline Leader
1. GENERAL
1.01 | Evaluate Existing Facility Operations | x | [9 empty] | R
1.02 | Participate on Design & Construction Commissioning Team | x | x | x | x | x | x | x | x |  |  | R
1.03 | Engage Operations Commissioning Team |  |  |  |  | x | [5 empty] | R |  |  |  | x
1.04 | Operations Commissioning Plan |  |  |  |  | x | x |  | x |  | x | R | x | x | x | x
1.05 | Annual Operations Commissioning Review & Plan Update | [8 empty] | x |  | R |  |  |  | x
1.06 | Annual Operations Commissioning Report | [8 empty] | x |  | R |  |  |  | x
1.07 | New Employee Training Program | [8 empty] | x |  | R
1.08 | Submit Outcome Documentation | x | x |  |  | x | x | x | x | x |  | x |  |  |  | R
1.09 | Next Use | [8 empty] | x |  | R
2. SYSTEM TURNOVER PROCESS FROM CONSTRUCTION TO OPERATIONS
2.01 | Define Turnover Prerequisites | [5 empty] | x |  |  |  | x | R | x
2.02 | Define Authority for Official Acceptance & Turnover | [5 empty] | x |  |  |  |  | R
2.03 | Operations Team Familiarization with Project Documentation and Systems | [6 empty] | x |  |  |  | R
2.04 | Complete Systems Transfer from Contractors to Operators | [7 empty] | x |  |  | R
3. PROBLEM RESPONSE PLAN
3.01 | Problem Documentation Process | [6 empty] | x |  |  |  | R
3.02 | Problem Response Process | [6 empty] | x |  |  |  | R
3.03 | Problem Resolution Documentation Process | [6 empty] | x |  |  |  | R
3.04 | Implementation | [7 empty] | x | x |  | R
3.05 | Annual Evaluation and Reporting | [7 empty] | x | x |  | x |  |  |  | R
4. MAINTENANCE PLAN
4.01 | Cleaning Products and Practices | [6 empty] | x |  |  |  | R
4.02 | Cleaning Products Documentation | [6 empty] | x |  |  |  | R
4.03 | Moisture Prevention Practices | [6 empty] | x |  |  |  | R
4.04 | Moisture Response Practices | [6 empty] | x |  |  |  | R
4.05 | Moisture Control Documentation | [6 empty] | x |  |  |  | R
4.06 | Preventive Maintenance Activities | [6 empty] | x |  |  |  | R
4.07 | Preventive Maintenance Documentation | [6 empty] | x |  |  |  | R
4.08 | Implementation | [7 empty] | x | x |  | R
4.09 | Annual Building IAQ Performance Evaluation | [8 empty] | x |  | R
4.10 | Annual Evaluation and Reporting | [7 empty] | x | x |  | x |  |  |  | R
5. ENERGY EFFICIENT OPERATIONS MANUAL (IN DEVELOPMENT - RECOMMENDED)
5.01 | System Descriptions | [6 empty] | x |  |  | x |  | R
5.02 | As built Control Drawings and Sequences of Operation | [7 empty] | x |  | x |  |  | R
5.03 | Time of Day Schedules and Plan for Assessing their Relevance | [5 empty] | x | x |  |  |  | R |  | x
5.04 | Seasonal Considerations | [5 empty] | x | x |  |  | x | R | x | x
5.05 | Recalibration Schedule | [6 empty] | x |  |  | x | x |  | R
5.06 | Adjustable Setpoints and Plan for Assessing their Relevance | [6 empty] | x |  |  |  | R |  | x
5.07 | Recommissioning Tests | [6 empty] | x |  |  | x | R
5.08 | Allocation of Building Energy | [5 empty] | x | [7 empty] | R
5.09 | Energy System Diagrams | [6 empty] | x |  |  | R |  | x | x
5.10 | Expected Performance Graph-Diagnostic Diagrams | [6 empty] | x |  |  | R |  | x
5.11 | Facility Work Order Verification Documents | [6 empty] | x |  | x | R
5.12 | Implementation | [7 empty] | x | x |  | R
5.13 | Annual Evaluation and Reporting | [7 empty] | x | x |  | x |  |  |  | R
6. CORRECTION PERIOD USER COMFORT AND SATISFACTION ASSESSMENT
6.01 | B3 Post Occupancy Evaluation Process (POE) | [6 empty] | x |  |  |  | R
6.02 | 9 Month Occupant Sustainable Post Occupancy Survey (SPOES) | [7 empty] | x |  |  | R
6.03 | 18 Month Occupant Sustainable Post Occupancy Survey (SPOES) | [7 empty] | x |  |  | R